## Tracker1
Country | Responsible | Status | Comments
Germany | Don | Ongoing
India | Suresh | Not Started
USA | Christian | Completed
Norway | Finn Allen | Ongoing
Australia | Warner | Completed

## Tracker2
No. | Task | Responsible | Status | Completion %
1 | Create a Login frontend page | Suresh | Completed | 100%
2 | Create a Login backend page | Symonds | Ongoing | 20%
3 | Create the database for the login | Rohit | Ongoing | 50%
4 | Test the login page | Andrew | Not Started | 0%
5 | Create a Register frontend page | Suresh | Completed | 100%
6 | Create a Register backend page | Symonds | Ongoing | 40%
7 | Create the database for the Register | Rohit | Ongoing | 60%
8 | Test the Register page | Andrew | Not Started | 0%
9 | Create the web page | Suresh | Not Started | 0%
10 | Add the items inside the page | Henry | Not Started | 0%
11 | Create the cart page | Suresh | Not Started | 0%
12 | Create the payment page | Suresh | Not Started | 0%
13 | Test the backend cart page | Andrew | Not Started | 0%
14 | Add customer data in the database | Rohit | Not Started | 0%
15 | Test the web application | Andrew | Not Started | 0%
|  |  | Total Completion % | 24.67%

## Tracker3
Recruitment process project management
N | Name of New Employee | Status |  |  | Comments
|  | Recruitment | Onboarding | System Accesses
1 | Jerry | Completed | Completed | Completed
2 | Kishore | Completed | Completed | Completed
3 | Henry | Completed | Completed | Ongoing
4 | Vishal | Completed | Ongoing | Ongoing
5 | Rahul | Ongoing | Ongoing | Ongoing
6 | Christian | Ongoing | Not Started | Not Started
7 | Joseph | Not Started | Not Started | Not Started
8 | Lokesh | Not Started | Not Started | Not Started

## Tracker4
PM Log
N | Actions | Action / Issue | Owner | Due date | Status | Comment
1 |  | Action | Frank | 2025-05-05 | Completed
2 |  | Action | Henry |  | Completed
3 |  | Issue | Henry |  | Completed
4 |  | Action | Henry |  | Ongoing
5 |  | Issue | Henry |  | Ongoing
6 |  | Issue | Kishore |  | Not Started
7 |  | Issue | Kishore |  | Not Started
8 |  | Issue | Kishore |  | Not Started
9 |  | Action | Jerry |  | Ongoing
10 |  | Action | Jerry |  | Ongoing
Action / Issue / Dependency Log
N | Actions | Action / Issue / Dependency | Owner | Due date | Status | Comment
1 |  | Action | Frank | 2025-05-05 | Completed
2 |  | Action | Henry |  | Completed
3 |  | Dependency | Henry |  | Completed
4 |  | Action | Henry |  | Ongoing
5 |  | Dependency | Henry |  | Ongoing
6 |  | Issue | Kishore |  | Not Started
7 |  | Issue | Kishore |  | Not Started
8 |  | Issue | Kishore |  | Not Started
9 |  | Action | Jerry |  | Ongoing
10 |  | Action | Jerry |  | Ongoing
RAIDD Log
N | Actions | Risk / Action / Issue / Dependency / Decision (RAIDD) | Owner | Due date | Status | Comment
1 |  | Action | Frank | 2025-05-05 | Completed
2 |  | Action | Henry |  | Completed
3 |  | Dependency | Henry |  | Completed
4 |  | Action | Henry |  | Ongoing
5 |  | Dependency | Henry |  | Ongoing
6 |  | Issue | Kishore |  | Not Started
7 |  | Issue | Kishore |  | Not Started
8 |  | Decision | Kishore |  | Not Started
9 |  | Action | Jerry |  | Ongoing
10 |  | Action | Jerry |  | Ongoing

## Tracker5
N | Activity | Start Date | End Date | Status
1 | Requirement analysis | 2025-12-23 | 2026-01-06 | Completed
1.1 | Project plan | 2025-12-23 | 2025-12-29 | Completed
1.2 | Functional requirment | 2025-12-30 | 2026-01-05 | Completed
2 | Planning | 2026-01-07 | 2026-01-13 | At Risk
2.1 | Application Planning | 2026-01-07 | 2026-02-12 | Ongoing | RAG Status [Red, Amber, Green]
3 | Coding | 2026-02-12 | 2026-03-15 | Ongoing | * The activity is delayed
3.1 | Coding part A | 2026-02-12 | 2026-02-19 | Completed | * there is risk not to achieve the due date
3.2 | Coding part B | 2026-02-19 | 2026-02-28 | Not Started | * Work is progressingly normal
3.3 | Coding part C | 2026-03-01 | 2026-03-14 | Ongoing
4 | Testing | 2026-03-17 | 2026-04-04 | Delayed
4.1 | STLC | 2026-03-18 | 2026-04-02 | Not Started
5 | Environmental setup | 2026-04-06 | 2026-04-12 | Not Started
6 | Exceution | 2026-04-15 | 2026-05-20 | At Risk
6.1 | Execute the tested code | 2026-04-17 | 2026-05-02 | Ongoing
6.2 | Bug Report | 2026-05-04 | 2026-05-12 | Ongoing
6.3 | Analytical Report | 2026-05-13 | 2026-05-19 | Ongoing
7 | Closure | 2026-05-22 | 2026-06-01 | Not Started
7.1 | Final Report | 2026-05-23 | 2026-06-29 | Not Started

## Tracker6
N | Activity | Start Date | End Date | 2025 |  | 2026
|  |  |  | Dec |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun
|  |  |  | 2026-12-22 | 2026-12-29 | 2027-01-05 | 2027-01-12 | 2027-01-19 | 2027-01-26 | 2027-02-02 | 2027-02-09 | 2027-02-16 | 2027-02-23 | 2027-03-02 | 2027-03-09 | 2027-03-16 | 2027-03-23 | 2027-03-30 | 2027-04-06 | 2027-04-13 | 2027-04-20 | 2027-04-27 | 2027-05-04 | 2027-05-11 | 2027-05-18 | 2027-05-25 | 2027-06-01 | 2027-06-08 | 2027-06-15 | 2027-06-22
1 | Requirement analysis | 2025-12-23 | 2026-01-06 | bar: 2026-12-22 to 2027-01-05
1.1 | Project plan | 2025-12-23 | 2025-12-29 | bar: 2026-12-22 to 2026-12-29
1.2 | Functional requirment | 2025-12-30 | 2026-01-05 | bar: 2027-01-05
2 | Planning | 2026-01-07 | 2026-02-12 | bar: 2027-01-12 to 2027-02-16
2.1 | Application Planning | 2026-01-07 | 2026-02-12 | bar: 2027-01-12 to 2027-02-16
3 | Coding | 2026-02-12 | 2026-03-15 | bar: 2027-02-16 to 2027-03-16
3.1 | Coding part A | 2026-02-12 | 2026-02-19 | bar: 2027-02-16 to 2027-02-23
3.2 | Coding part B | 2026-02-19 | 2026-02-28 | bar: 2027-02-23
3.3 | Coding part C | 2026-03-01 | 2026-03-14 | bar: 2027-03-02 to 2027-03-16
4 | Testing | 2026-03-17 | 2026-04-04 | bar: 2027-03-16 to 2027-04-06
4.1 | STLC | 2026-03-18 | 2026-04-02 | bar: 2027-03-16 to 2027-04-06
5 | Environmental setup | 2026-04-06 | 2026-04-12 | bar: 2027-04-06 to 2027-04-13
6 | Exceution | 2026-04-15 | 2026-05-20 | bar: 2027-04-13 to 2027-05-18
6.1 | Execute the tested code | 2026-04-17 | 2026-05-02 | bar: 2027-04-13 to 2027-05-04
6.2 | Bug Report | 2026-05-04 | 2026-05-12 | bar: 2027-05-04 to 2027-05-11
6.3 | Analytical Report | 2026-05-13 | 2026-05-19 | bar: 2027-05-11 to 2027-05-18
7 | Closure | 2026-05-22 | 2026-06-20 | bar: 2027-05-18 to 2027-06-15
7.1 | Final Report | 2026-05-23 | 2026-06-18 | bar: 2027-05-18 to 2027-06-15

## Budget1
N | Materials | Unit Type | Budget Price Per Unit | Amount(Nos) | Budget | Actual price per unit | Actual | Balance
1 | Cables | Meter | 80 | 20 | 1600 | 90 | 1800 | -200
2 | Pipes | Meter | 165 | 24 | 3960 | 180 | 4320 | -360
3 | Oil | liter | 60 | 10 | 600 | 50 | 500 | 100
4 | Nut & Bolt | Kg | 90 | 5 | 450 | 70 | 350 | 100
5 | Engineer Services | Daily rate | 600 | 2 | 1200 | 800 | 1600 | -400
6 |  |  |  |  | 0 | 0 | 0 | 0 | Budget | 7810
7 |  |  |  |  | 0 | 0 | 0 | 0 | Actual | 8570
8 |  |  |  |  | 0 | 0 | 0 | 0 | Balance | -760
9 |  |  |  |  | 0 | 0 | 0 | 0
10 |  |  |  |  | 0 | 0 | 0 | 0
11 |  |  |  |  | 0 | 0 | 0 | 0
12 |  |  |  |  | 0 | 0 | 0 | 0
13 |  |  |  |  | 0 | 0 | 0 | 0
|  |  |  | Total | 7810 |  | 8570 | -760